PROJECT ASSESSMENT TYPE

- SCOPE

This work instruction establishes a Project Type using a risk based assessment.  The Project Assessment Type is completed as part of the 0300-0310-005-C PROJECT INITIATION procedure within 0300-0300-005-B PROJECT MANAGEMENT PROCESS.  The approach is to classify a project using core risk assessment areas related to the State Chief Information Officer’s (SCIO) mission, major project lessons learned, as well as a project’s cost, schedule, resource availability and security impact.  This information is used to identify and communicate to Business Owners and all other key stakeholders the potential barriers that may prevent a project from achieving stated objectives.  Project typing is reviewed and updated throughout the project life-cycle to continually drive leadership awareness and decision-making.

- OWNER

  - The State Chief Information Officer (SCIO) owns this procedure.  No changes, additions or alterations may be made without the owner’s written approval.

- REFERENCE DOCUMENTS

| DOCUMENT IDENTIFICATION | DOCUMENT TITLE |
| --- | --- |
| NC General Statute 147, Article 15 | DEPARTMENT OF INFORMATION TECHNOLOGY |
| Data Classification Policy | DATA CLASSIFICATION POLICY |
| 0100-0800-010-B | FORMS AND RECORDS CONTROL |
| 0300-0300-005-B | PROJECT MANAGEMENT PROCESS |
| 0300-0310-005-C | PROJECT INTIATION |
| 0300-0330-010-C | PROJECT GO-LIVE READINESS ASSESSMENT |
| 0300-0360-005-C | PROJECT CHANGE REQUEST |
| 0300-0375-005-C | PROGRAM/PROJECT REVIEW |

- ASSOCIATED FORMS

| FORMS IDENTIFICATION | FORM TITLE |
| --- | --- |
| 0300-0310-020-D | PROJECT ASSESSMENT TYPE FORM |
| 0810-0810-005-D | QUALITY CONTROL DECISION POINTS |

5.0	DEFINITIONS

- NONE

- PROCEDURE

The Project Assessment Type is a “snapshot” risk assessment rating of an IT Project that can be updated throughout the project life-cycle.  The Project Assessment Type is a key component of the project Business Case.

NOTE: The Project Assessment Type Form is completed as a project detail page in the Touchdown System, but these forms can be used by Project Managers as a template.

  - Project Initiation Phase - Type Identification

    - During the Project Initiation phase the agency Project Manager (PM), in conjunction with the Business Owner, will complete the 0300-0310-020-D PROJECT ASSESSMENT TYPE FORM and upload the document into the Project Site Document Library in the TOUCHDOWN System.

    - The 0300-0310-020-D PROJECT ASSESSMENT TYPE FORM consists of eight (8) “Risk Assessment Area” criteria to be rated as “Low”, “Medium” or “High” risk based on a weighted scale.  For each of the Risk Assessment Areas, fill in the value from 1-5 that reflects the risk rating for this project.

      - Estimated Project Budget

      - Estimated Project Duration

      - Business Owner Involvement

      - Impact to Owning Organization

      - Impact to Citizens, Business or Industry

      - Required due to Legislation or Mandates

      - Resource Availability (Skills, Availability, Commitment, Over allocation, Dependency on External Agencies)

      - Sensitive Info (Data Classification) - use Public for Low, Restricted for Medium and Highly Restricted for High –this coincides with the Data classification policy https://it.nc.gov/document/statewide-data-classification-and-handling-policy.

Note: Required due to Legislation or Mandates is a “Yes” or “No” question with “Yes” receiving the highest weight.

    - Security Data Classification - The classification of the data in the system. This based on the ESRMO Data DATA CLASSIFICATION POLICY.  If the classification is “medium” or “high” then a PROJECT GO-LIVE READINESS ASSESSMENT must be completed.

    - The “Total” is the weighted sum of the “Rating” scores.  Per the “Project Type / Total Rating Range” table: Project Total Rating of 85-165 indicates “Low” risk; Project Total Rating of 166-330 indicates “Medium” risk; and, Project Total Rating of 331-500 indicates “High” risk.

Note: Projects with a total project budget/cost greater than $10M and identified as “High” risk per this work instruction will require independent review and validation of the cost estimates.

    - If a discrepancy exists in the “Project Total Rating” and/or “Project Type” on the completed 0300-0310-020-D PROJECT ASSESSMENT TYPE FORM, the Enterprise Project Management Office (EPMO) Project Management Advisor (PMA) will review the findings with the PM.

    - The EPMO will review and validate the completed 0300-0310-020-D PROJECT ASSESSMENT TYPE FORM as part of 0300-0310-005-C PROJECT INITIATION.

  - Project Life-Cycle - Type Identification

    - Throughout the Project Life-Cycle, the agency PM will update the 0300-0310-020-D PROJECT ASSESSMENT TYPE FORM following the same procedure identified in 6.1.2 - 6.1.5 above.  Examples of events that may require an update to the 0300-0310-020-D PROJECT ASSESSMENT TYPE FORM include:

      - Initiating a Change Request per 0300-0360-005-C PROJECT CHANGE REQUEST

      - Reaching a Decision Point per 0810-0810-005-D QUALITY CONTROL DECISION POINTS

      - Entering a new Project Phase (I.e. Initiation; Planning and Design; Execution and Build; Implementation; or, Closeout)

      - Preparing for a 0300-0375-005-C PROGRAM/PROJECT REVIEW

      - Preparing for a 0300-0330-010-C PROJECT GO-LIVE READINESS ASSESSMENT

- RECORDS

  - Unless otherwise specified in this Procedure/QWI, Records shall be maintained in accordance with

0100-0800-010-B FORMS AND RECORDS CONTROL procedure.

- REASON FOR CHANGE

  - Corrected cross reference errors in section 3.0 REFERENCE DOCUMENTS.  Updated paragraphs 6.1.2 and 6.1.3 to reflect revised Assessment Area Rating Scale and Total Rating Ranges.

  - Corrected cross reference errors in section 3.0 REFERENCE DOCUMENTS.  Updated section 6.0 PROCEDURE to add clarification.

  - Updated Legislation Information.

  - Change assessment question from 11 to 8.

  - Added new weighting of assessment questions.

  - Removed delegation authority.

  - Clarified meaning of Required due to Legislation or Mandates.

  - Remove Project Decision Memo, no longer used.

  - Changed the Security Risk Criteria.

  - Added Security Data Classification and process for “Medium” or “High” classification to require the project manager to complete a Go-Live Readiness Assessment.