PROJECT EXECUTION AND BUILD

- SCOPE

This Quality Work Instruction (QWI) defines the Project Execution and Build procedure as the method to effectively build, configure and/or customize a product or service based on business requirements, within the overarching 0300-0300-005-B PROJECT MANAGEMENT PROCESS.  This procedure results in completion of Information Technology (IT) Project deliverables that must be fully tested prior to Business Owner acceptance.

- OWNER

  - The Enterprise Project Management Office (EPMO) Director owns this QWI.  No changes, additions or alterations may be made without the owner’s written approval.

- REFERENCE DOCUMENTS

| DOCUMENT IDENTIFICATION | DOCUMENT TITLE |
| --- | --- |
| 0100-0800-010-B | FORMS AND RECORDS CONTROL |
| 0300-0300-005-B | PROJECT MANAGEMENT PROCESS |
| 0300-0310-005-C | PROJECT INITIATION |
| 0300-0330-010-C | PROJECT GO-LIVE READINESS ASSESSMENT |
| 0300-0360-005-C | PROJECT CHANGE REQUEST |
| 0600-0600-005-B | CORRECTIVE ACTION PROCESS |
| 0810-0810-005-B | QUALITY CONTROL PROCESS |

- ASSOCIATED FORMS

| FORMS IDENTIFICATION | FORM TITLE |
| --- | --- |
| 0300-0330-010-D | PROJECT GO-LIVE READINESS ASSESSMENT FORM |
| 0300-0360-015-D | PROJECT CHANGE REQUEST FORM |
| 0810-0810-005-D | QUALITY CONTROL DECISION POINTS |

- DEFINITIONS

- AGENCY THRESHOLD:  see Glossary of Terms and Definitions

- EPMO THRESHOLD:  see Glossary of Terms and Definitions

- PROCEDURE

The Project Execution and Build Phase is where the Project Manager (PM) and the project team executes the project plan to build, test and prepare a solution for implementation.  Throughout this phase the baseline project schedule and costs are monitored in accordance with 0810-0810-005-B QUALITY CONTROL PROCESS.

  - The PM drives all aspects of the IT Project while managing schedule execution and cost control.

  - The Project Management Advisor (PMA) will follow the 0600-0600-005-B CORRECTIVE ACTION PROCESS if project cost or schedule variance exceeds an established EPMO threshold as documented in the 0300-0360-005-C PROJECT CHANGE REQUEST process.

  - If required, the PM will follow the 0300-0360-005-C PROJECT CHANGE REQUEST process.

  - The project team builds, configures and tests the solution, and gains Business Owner acceptance.

  - If required, the PM will initiate the 0300-0330-010-C PROJECT GO-LIVE READINESS ASSESSMENT procedure and Go-Live Readiness Decision Point (DP) as defined in 0810-0810-005-D QUALITY CONTROL DECISION POINTS.  The Agency Chief Information Officer (Agency CIO) must approve the Go-Live Readiness Assessment before the project can move into the Implementation Phase.

  - If required, the EPMO provides Corrective Action requirements in accordance with the 0600-0600-005-B CORRECTIVE ACTION PROCESS.

- RECORDS

7.1	Unless otherwise specified in this Procedure/QWI, Records shall be maintained in accordance with

0100-0800-010-B FORMS AND RECORDS CONTROL procedure.

8.0	REASON FOR CHANGE

8.1	Corrected errors in section 3.0 REFERENCE DOCUMENTS and section 4.0 ASSOCIATED FORMS.

8.2	Change EPMO Manager to EPMO Director.